## Slide 1: TEST PLANNING, MANAGEMENT, EXECUTION, AND REPORTING
UNIT-5
By: Anand C Unakal

## Slide 2
TESTING PLANNING
It is rightly sad that “ Failing to plan is planning to fail ”.
Therefore testing also requires proper planning for appropriate execution.
Testing planning includes:
Preparing a Test Plan
2. Scope Management: deciding Features to be Tested/Not tested
3. Deciding Test Approach/Strategy
4. Setting up Criteria for Testing

## Slide 3
6. Identifying Resources requirements
7. Identifying Test Deliverables
8. Testing Tasks : Size and Effort Estimation
9. Activity Breakdown and Scheduling
10. Communication Management
11. Risk Management

## Slide 4: TESTING PLANNING
Preparing a Test Plan
Testing – like any project – should be driven by a plan. The test plan acts as the anchor for the execution, tracking, and reporting of the entire testing project and covers
What needs to be tested
How the testing is going to be performed
What resources are needed for testing
The time lines by which the testing activities will be performed.
Risks that may be faced in all of the above.

## Slide 5
2. Scope Management : Deciding Features to be Tested/Not Tested
Scope management pertains to specifying the scope of a project. For testing, scope management entails
Understanding what constitutes a release of a project;
Breaking down the release into features;
Prioritizing the features for testing;
Deciding which features will be tested and which will not be; and
Gathering details to prepare for estimation of resources for testing.

## Slide 6
The following factors drive the choice and prioritization of features to be tested.
Features those are new and critical for the release.
Features whose failures can be catastrophic.
Features that are expected to be complex to test.
Features which are extensions of earlier features that have been defect prone.

## Slide 7
3. Deciding test approach/strategy
This include identifying
What type of testing would you use for testing functionality?
What are the configurations or scenarios for testing the feature?
What integration testing would you do to ensure these features work together?
What localization validations would be needed?
What “non-functional” tests would you need to do?

## Slide 8
4. Setting up Criteria for Testing
There must be clear entry and exit criteria for different phases of testing. There may also be entry criteria for the entries testing activity to start. The completion/exit criteria specify when a test cycle or a testing activity can be deemed complete.

## Slide 9
5. Identifying Responsibilities, Staffing, and Training Needs
These different roles should complement each other. The different role definitions should
Ensure there is clear accountability for a given task, so that each person knows what he or she has to do;
Clearly list the responsibilities for various functions to various people, so that everyone knows how his or her work fits into the entire project;
Complement each other, ensuring no one steps on an others toes; and
Supplement each other, so that no task is left unassigned.

## Slide 10
6. Identifying Resource Requirements
Some of the following factors need to be considered.
Machine configuration (RAM, processor, disk, and so on) needed to run the product under test.
Overheads required by the test automation tool, if any.
Supporting tools such as compilers, test data generators, configuration management tools, and so on.
The different configurations of the supporting software (for example, OS) that must be present

## Slide 11
7. Identifying Test Deliverables
The deliverables includes the following, all reviewed and approved by the appropriate people.
The test plan itself (master test plan, and various other test plans for the project)
Test case design specifications
Test cases, including any automation that is specified in the plan.
Test logos produced by running the tests
Test summary reports.

## Slide 12
8. Testing Tasks: Size and Effort Estimation
The scope identified above gives a broad overview of what needs to be tested. This understanding is quantified in the estimation step. Estimations happens broadly in three phases.
Size estimation
Effort estimation
Schedule estimation.

## Slide 13
Size estimation: It quantifies the actual amount of testing that needs to be done several factors contribute to the size estimate of testing project.
Size of the product under test. This obviously determines the amount of testing that needs to be done. The larger the product, in general, grater is the size of testing to be done. Some of the measurement of the size of product under test are as follows;
Line of Code (LOC).
A function point (FP).
No of screens reports or transactions.

## Slide 14
Extent of automation required when automation is involved, the size of work to be done for testing increases.
Number of platforms and inter-operability environments to be tested. If a particular product is to be tested under several different platforms or under several different configurations, then the size of the testing task increases.

## Slide 15
Effort Estimation: Estimating effort is important because often effort has a more direct influence on cost than size. The other factors that drive the effort estimate are as follows:
Productivity data:
Reuse opportunities :
Robustness of process:
For example;
  Well-documented standards for writing test specifications, test scripts etc.
  Proven process for performing functions such as reviews and audits;
  Consistent ways of training people, and
  Objective ways of measuring the effectiveness of compliance to process

## Slide 16
9. Activity Breakdown and Scheduling
The following steps make up this translation.
Identifying external and internal dependencies among the activities.
Sequencing the activities, based on the expected duration as well as on the dependencies.
Identifying the time required for each of the WBS activities, taking into account the above two factors
Monitoring the progress in terms of time and effort
Rebalancing schedules and resources as necessary.
External dependencies of an activity
Internal dependencies
Scheduling:

## Slide 17
10. Communications Management
Communications management consists of evolving and following procedures for communication that ensure that everyone is kept in sync with the right level of detail.
11. Risk Management
Risks are uncertain events that could potentially affect a project’s outcome. Risk management entails
Identifying the possible risks
Quantifying the risks;
Planning how to mitigate the risks; and
Responding to risks when they become a reality

## Slide 18
11. Risk Management
Risk
identification
Risk
response
Risk
quantification
Risk mitigation
planning

## Slide 19
Project Management

## Slide 20
Risk identification
Risk quantification
Risk mitigation planning
Risk response
The following are some of the common risks encountered in testing projects and their characteristics.
Unclear requirements
Schedule dependence
Insufficient time for testing
“Show stopper” defects.
Availability of skilled and motivated people for testing.
Inability to get a test automation tool.

## Slide 21: TEST MANAGEMENT
Test management includes :
Choice of Standards
Test Infrastructure Management
Test People Management
Integrating with Product Release

## Slide 22
Choice of Standards
Internal standards are standards formulated by a testing organization to bring in consistency and predictability.
Naming and storage conventions for test artifacts
Document standards
Test coding standards and
Test reporting standards.

## Slide 23
2. Test Infrastructure Management
Testing requires a robust infrastructure to be planned upfront. This infrastructure is made up of three essential elements.
A test case database (TCDB).
A defect repository
Configuration management repository and tool.
A test case database captures all the relevant information about the test cases in an organization. A defect repository captures all the relevant details of defects reported for a product . An SCM repository also known as (CM repository) keeps track of change control and version control of all the files/entities that make up a software product.

## Slide 24
3. Test People Management
Developer : These testing folks.... they are always nitpicking!
Tester : Why don’t these developers do any thing right?!
Sales person: When will I get a product out that I can sell?!
People management is an integral part of any project management. People management also requires the ability to hire, motivate, and retain the right people. These skills are seldom formally taught (unlike technical skills).

## Slide 25
4. Integrating with Product Release
Ultimately, the success of a product depends on the effectiveness of integration of the development and testing activities. The schedules of testing have to linked directly to product release. The following are some of the points to be decided for this planning.
Sync points between development and testing as to when different types of testing can commence.
Service level agreements between development and testing as to how long it would take for the testing team to complete the testing.

## Slide 26: TEST PROCESS
The methodology to perform testing is as follows :
Putting Together and Baselining a Test Plan.
Test Case Specification
Update of Traceability Matrix
Identifying Possible Candidates for Automation
Developing and Baselining Test Cases
Executing Test Cases and Keeping Traceability Matrix Current
Collecting and Analysing Metrics
Preparing Test Summary Report
Recommending Product Release Criteria

## Slide 27
Putting Together and Baselining a Test Plan :
An organization normally arrives at a template that is to be used across the board. Each testing project puts together a test plan based on the template.
The test plan is reviewed by a designated set of competent people in the organization. It then is approved by a competent authority.
After this, the test plan is baselined into the configuration management repository. From then on, the baselined test plan becomes the basis for running the testing project.

## Slide 28
2. Test case Specification :
Hence, a test case specification should clearly identify;
The purpose of the test: This lists what feature or part the test is intended for.
Items being tested, along with their version/release numbers as appropriate.
Environment that needs to be set up for running the test case.
Input data to be used for the test case.
Steps to be followed to execute the test: If automated testing is used, then, these steps are translated to the scripting language of the tool.
The expected results that are considered to be “correct results”
A step to compare the actual results produced with the expected result

## Slide 29
3. Update of Traceability Matrix:
As discussed earlier, Black Box Testing, a requirements traceability matrix ensures that the requirements make it through the subsequent life cycle phases and do not get orphaned mid-course.
4. Identifying Possible Candidates for Automation:
The test case design forms the basis for writing the test cases. Some of the criteria that will be used in deciding which scripts to automate include.
Repetitive nature of the test;
Effort involved in automation;
Amount of manual intervention required for the test; and
Cost of automation tool.

## Slide 30
5. Developing and Baselining Test Cases :
Based on the test case specifications and the choice of candidates for automation, test cases have to be developed. The test cases should also have change history documentation, which specifies
What was the change?
Why the change was necessitated?
Who made the change?
When was the change made?
A brief description of how the change hasbeen implemented and
Other files affected by the change.

## Slide 31
6. Executing Test Cases and Keeping Traceability Matrix Current
The prepared test cases have to be executed at the appropriate times during a project. As the test cases are executed during a test cycle, the defect repository is updated with:
Defects from the earlier test cycles that are fixed in the current build.
New defects that get uncovered in the current run of the tests.

## Slide 32
7. Collecting and Analysing Metrics
When tests are executed, information about test execution gets collected in test logs and other files. The basic measurements from running the tests are then converted to meaningful metrics.
8. Preparing Test Summary Report
At the completion of a test cycle, a test summary report is produced. This report gives insights to the senior management about the fitness of the product for release.

## Slide 33
9. Recommending Product Release Criteria
One of the purposes of testing is to decide the fitness of a product for release. An evidence of what defects exist in the product, their severity and impact is reported to the senior management and the product release team as follows:
What defects the product has
What is the impact/severity of each of the defects
What would be the risks of releasing the product with the existing defects
The senior management can then take a meaningful business decision on whether to release a given product or not.

## Slide 34: TEST REPORTING
There are three types of reports or communication that are required:
Test incident report
Test cycle report
A test cycle report, at the end of each cycle gives:
  A summary of the activities carried out during that cycle.
  Defects those were uncovered during that cycle.
  Progress from the previous cycle to the current cycle in terms of defects fixed.
  Outstanding defects that are yet to be fixed in this cycle.
  Any variations observed in effort or schedule.

## Slide 35
3. Test summary report:
There are two types of test summary report:
  Phase-wise test summary, which is produced at the end of every phase.
  Final test summary report.
Recommending Product Release:
Based on the test summary report, an organisation can take a decision on whether to release the product or not.

## Slide 36
BEST PRACTICES
Best practices in testing can be classified into three categories:
Process related
People related
Technology related

## Slide 37
Thank You